## Sheet1
InterCollege Techfest Project Building
S. No. |  |  | Start Date
|  |  | 2020-01-20 |  | January
| Name | Performing roles in the tech fest memberwise | Plan Start | Plan End | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08
|  |  | Actual Start | Actual End | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
1 | Rohit Kumar | Java Programming | 2020-01-20 | 2020-02-04
|  |  | 2020-01-24 | 2020-02-08
2 | Aditya Gupta | Python Programming | 2020-01-23 | 2020-02-09
|  |  | 2020-01-21 | 2020-02-07
3 | Aadhar Goel | HTML, CSS, Javascript | 2020-01-23 | 2020-02-01
|  |  | 2020-01-20 | 2020-02-05
4 | Nischay Bhatia | Backend Developer | 2020-01-23 | 2020-02-08
|  |  | 2020-01-25 | 2020-02-06
5 | Mitesh Kumar | Personality Development | 2020-01-21 | 2020-02-08
|  |  | 2020-01-26 | 2020-02-05
6 | Krish Kumar | Communication Skills | 2020-01-20 | 2020-02-07
|  |  | 2020-01-23 | 2020-02-08
7 | Deepak Kumar | Project Manager | 2020-01-20 | 2020-02-06
|  |  | 2020-01-22 | 2020-02-01

## Sheet2
A learning observation while performing this gantt chart project.
A Gantt chart is a bar chart that outlines the tasks required to complete a project and their corresponding timelines. It is a useful tool for project planning and tracking, as it provides an overview of a project’s activities and progress . Here are some advantages of using a Gantt chart in project management:
1. Streamlined overview: A Gantt chart provides an overall perspective of a project and its timeline, making it easy to understand for both those who are deeply involved and those with less participation, such as executives and other stakeholders.
2. Efficiency and resource management: A Gantt chart can help ensure that leaders and workers manage their time and resources effectively. Project leaders can use it to set realistic schedules and allocate resources based on those schedules, including assigning the right people to the right tasks. It can also help project members come up with workarounds for potential problems before a project starts.
3. Better tracking: A Gantt chart enables project leaders and members to closely track tasks, benchmarks, and overall workflow. The chart can reveal possible constraints or issues and allow project leaders and members to adjust accordingly.
In my Gantt project planner, I observed that the chart helped me visualize the critical path, set baselines for project scope, budget, and schedule, and track project progress after kickoff 2. It also helped me manage my time and resources effectively, and come up with workarounds for potential problems before the project started.
I hope this helps! Let me know if you have any more questions.